## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Student Data Analysis
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2023-07-31
EXPECTED COMPLETION DATE | 2023-09-30
ESTIMETED COST | NA
GOALS, OBJECTIVE, DELIVERABLES
PROJECT OBJECTIVE | The main purpose of this initiative is to conduct a comprehensive analysis of our student interns, with the goal of gaining valuable insights into the intricate interplay between their academic performance, active participation in events, professional aspirations, and the various factors that contribute to their overall success within our organization.
BUSINESS CASE | Analysing Student Interns for Better Success Insights
GOALS/METRICS | Perform EDA to gain following insights unique students, Average GPA of the student, Students graduating by the end of 2024, Students who attended the events related to Data Science, Distribution of students across different graduation years, Top 5 Colleges with Most Students Knowing About the Event from Their Colleges, Top 5 Colleges with Highest Average GPA, Distribution of Students' Experience with Python Programming
EXPECTED DELIVERABLES | Exploratory data analysis
PROJECT SCOPE AND SHEDULE
WITHIN SCOPE | Scope: The project includes performing in-depth exploratory data analysis with the offered metrics in order to get insights into different aspects of student data. such as Academic performance, event participation, professional goals, and success-influencing aspects
OUTSIDE SCOPE | Predictive Analysis
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Shubham Gaikwad
SUPPORT RESOURCES | jupyter notebook, Python libraries: NumPy, Pandas, Matplotlib, Seaborn
COST ALLOCATION | 0
PROJECT STACKHOLDERS AND CUSTOMERS
PROCESS OWNER | Shubham Gaikwad
KEY STACKHOLDERS | Harshada Topale
END CUSTOMER | Cloud conselage Pvt Ltd
PROJECT RISKS, CONSTARINTS,ASSUMPTION
RISKS | Changes in Graduation Plans
ASSUMPTION | Data Reliability: The provided dataset is believed to be accurate and representative of the target audience.
CONSTARINTS | The actions of the team are guided by a preset set of criteria (unique students, GPA, graduation status, event attendance, and so on). The analysis will be limited to these parameters, potentially ignoring other significant elements.
MILESTONES
MILESTONES 1 - REQUIRMENT GATHERING | Achieved
MILESTONES 2 - PLANNING | Achieved
MILESTONES 3 - DESIGN | Achieved
MILESTONES 4 - DEVELOPMENT | Achieved
MILESTONES 5 - TESTING | Achieved
MILESTONES 6 - CLOSURE | Achieved