## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME |  |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2023-08-08 | Project Charter Approval Delay | Project Management | Yes | Streamline approval processes | Worked with stakeholders to expedite | Project Creator | Closed | Delay affected project kickoff
2 | 2023-08-11 | Inadequate Stakeholder Communication | Communication | Yes | Establish regular update meetings | Scheduled weekly stakeholder meetings | Project Manager | Closed | Stakeholders felt out of the loop.
3 | 2023-08-15 | Missing data in student records | Data management | Yes | Regular data quality checks and validation processes | Conducted data cleaning and verification | Project Creator | Closed | The missing data affected the accuracy of the analysis.
4 | 2023-09-11 | EDA Challenges | Data Analysis | Yes | Provide adequate training in EDA | Scheduled training sessions for the team | Project Approver /Project Manager | Closed | Team struggled with data visualization tools.
5 | 2023-09-23 | Missing Point in Final Report | Documentation | Yes | Implement rigorous data validation | Lead should conduct session on Appendix (Appendix Table) | Project Approver /Project Manager | Pending | Improved quality for final report