## RAID LOG
RAID Log
| Project title: | Student Data Analysis |  | Project Id: |  | Project Manager: | Harshada Topale
| DOCUMENT VERSION: |  |  | Last Updated date: | 2023-09-19 | Project Team Lead: | Shubham Gaikwad
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Data Integrity Risk | Loss of critical or sensitive data | Conducting data integrity checks and audits to identify and rectify any data inconsistencies | Shubham Gaikwad | Moderate | 3 | Closed | Risk
2 | Risk | Changes in Graduation Plans | delays in post-graduation plans such as securing a job or pursuing further education | Institutions should offer robust support services, including academic advising, to help students navigate any changes in graduation requirements effectively | Shubham Gaikwad | Low | 4 | Closed | Assumption
3 | Assumption | Data Reliability | If the provided dataset is inaccurate or not representative of the target audience, it can lead to wrong conclusions and strategic decisions being made based on incorrect or unreliable data. | Implement Data Quality Controls: Establish a robust process for data collection, cleaning, and validation to ensure accuracy and representativeness | Shubham Gaikwad | High | 2 | Closed | Issue
4 | Assumption | Relevance | If the relevance assumption is incorrectly applied, it can have a significant negative effect on decision-making and outcomes. | Implement strict data validation methods to ensure that information that is used in decision-making is accurate, up to date, and socially appropriate. | Shubham Gaikwad | High | 2 | Closed | Dependency
5 | Issue | Complexity of Data Analysis | If the analysis required to answer the 18 questions is not handled properly, it can cause project timetable delays and potentially incorrect outcomes. This is especially true when working with data and numerous factors. | Project Planning: Develop a comprehensive strategy that outlines the analysis's scope, time frame, and resources. | Shubham Gaikwad | High | 2 | Closed
6 | Issue | Incomplete or Missing Data | Incomplete data can reduce the overall quality and reliability of the analysis. | document missing data values or the reason for their absence to maintain transparency and aid in the analysis process. | Shubham Gaikwad | High | 2 | Closed | Open
7 | Dependency | Data Availability | Access to data is essential for the project's effective conclusion. If the data is unavailable or delayed, it can seriously affect the project's schedule and the feasibility of providing accurate answers. | Create a detailed data collection plan that specifies the sources, methods, and time frame for collecting the necessary data. Make sure the information sources are dependable and reachable. | Shubham Gaikwad | High | 2 | Closed | Closed
8 | Dependency | Data Analysis Tools | It directly impacts the ability to do data analysis, develop insights, and provide project-related insights. | Select dependable and trusted data analysis tools that have become known for their accuracy, adaptability, and dataset compatibility. | Shubham Gaikwad | High | 2 | Closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24