## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Progra 2023 - Data Analytics- Project Schedule
|  | PROJECT START DATE | 2023-07-31
|  | Display Week Sr No | 1 | [10 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25
 | time axis 2023-07-31 to 2023-10-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-07-31 to 2023-10-01
1 |  | Project Overview |  |  |  |  | 2023-07-31 | 2023-08-05
1.1 | Week 1 |  | Project Onboarding | - | Clearly defined goals and objectives for the onboarding process | Shubham Gaikwad | 2023-08-01 |  | 2023-08-01 | 1 | Completed | Task Finished | NA
1.2 | Week 1 |  | Study the problem | - | Understanding of customer pain points and challenges | Shubham Gaikwad | 2023-08-02 |  | 2023-08-02 | 1 | Completed | Task Finished | NA
1.3 | Week 1 |  | Understanding business problem | - | Prioritizing the most critical problems to address | Shubham Gaikwad | 2023-08-03 |  | 2023-08-03 | 1 | Completed | Task Finished | NA
1.4 | Week 1 |  | Identify business problem | - | Clearly defining the business problem statement | Shubham Gaikwad | 2023-08-04 |  | 2023-08-04 | 1 | Completed | Task Finished | NA
1.5 | Week 1 |  | Data Collection For Problem Statement | - | Access to relevant internal and external data sources | Shubham Gaikwad | 2023-08-05 |  | 2023-08-05 | 1 | Completed | Task Finished | NA
2 |  | Project Initiation |  |  |  |  | 2023-08-07 | 2023-08-19
2.1 | Week 2 |  | Filled a project charter | - | Weekly meeting | Shubham Gaikwad | 2023-08-07 |  | 2023-08-08 | 2 | Completed | Task Finished | NA
2.2 | Week 2 |  | requirement elicitation questionnaire | - | Weekly meeting | Shubham Gaikwad | 2023-08-09 |  | 2023-08-11 | 4 | Completed | Task Finished | NA
2.3 | Week 2 |  | Weekly Meeting Attended | - | Schedule and coordination of meeting times. | Shubham Gaikwad | 2023-08-12 |  | 2023-08-12 | 2 | Completed | Attended | NA
2.4 | Week 3 |  | SRS Document | - | Requirement Elicitation Questionnaire | Shubham Gaikwad | 2023-08-14 |  | 2023-08-16 | 3 | Completed | Task Finished | NA
2.5 | Week 3 |  | Attended requirement elicitation meeting | - | Requirement Elicitation Questionnaire and | Shubham Gaikwad | 2023-08-17 |  | 2023-08-17 | 2 | Completed | Attended | NA
2.6 | Week 3 |  | Weekly Meeting Attended | - | Schedule and coordination of meeting times. | Shubham Gaikwad | 2023-08-19 |  | 2023-08-19 | 2 | Completed | Attended | NA
3 |  | Project Planning |  |  |  |  | 2023-08-21 | 2023-09-02
3.1 | Week 4 |  | Work Breakdown structure | - | Availability of resources (e.g., team members, equipment, tools) | Shubham Gaikwad | 2023-08-21 |  | 2023-08-22 | 4 | Completed | Task Finished | NA
3.2 | Week 4 |  | Identify Risks | - | Collaboration and input from team members. | Shubham Gaikwad | 2023-08-23 |  | 2023-08-23 | 2 | Completed | Task Finished | NA
3.3 | Week 4 |  | Assumption | - | Understanding of project scope, objectives, and constraints. | Shubham Gaikwad | 2023-08-24 |  | 2023-08-24 | 2 | Completed | Task Finished | NA
3.4 | Week 4 |  | Weekly Meeting Attended | - | Schedule and coordination of meeting times. | Shubham Gaikwad | 2023-08-26 |  | 2023-08-26 | 2 | Completed | Attended | NA
3.5 | Week 5 |  | Project Sheduling | - | Availability of resources required for each task or activity | Shubham Gaikwad | 2023-08-28 |  | 2023-08-30 | 2 | Completed | Task Finished | NA
3.6 | Week 5 |  | Filled RAID log | - | Availability of a standardized template or tool for documenting RAID log. | Shubham Gaikwad | 2023-08-31 |  | 2023-09-01 | 3 | Completed | Task Finished | NA
3.7 | Week 5 |  | Started Filling Lessons Learnt Log | - | Reflection and analysis of project performance | Shubham Gaikwad | 2023-09-01 |  | 2023-09-02 | 3 | Completed | Task Finished | NA
3.8 | Week 5 |  | Weekly Meeting Attended | - | Schedule and coordination of meeting times. | Shubham Gaikwad | 2023-09-02 |  | 2023-09-02 | 2 | Completed | Attended | NA
4 |  | Project Execution |  |  |  |  | 2023-09-04 | 2023-09-16
4.1 | Week 6 |  | Finalized Goal / Metrics | - | Clear understanding of project objectives and key results | Shubham Gaikwad | 2023-09-04 |  | 2023-09-05 | 2 | Completed | Task Finished | NA
4.2 | Week 6 |  | Finalized Expected Deliverables | - | Detailed project scope and requirements documentation, collaboration with stakeholders to understand their expectations | Shubham Gaikwad | 2023-09-06 |  | 2023-09-07 | 2 | Completed | Task Finished | NA
4.3 | Week 6 |  | Finalized Resource | - | Identification of resources (human or technological) | Shubham Gaikwad | 2023-09-08 |  | 2023-09-08 | 1 | Completed | Task Finished | NA
4.4 | Week 6 |  | Weekly Meeting Attended |  | Schedule and coordination of meeting times. | Shubham Gaikwad | 2023-09-09 |  | 2023-09-09 | 2 | Completed | Attended | NA
4.5 | Week 7 |  | Started Performing EDA | Data Cleaning and Preparation | Data cleaning tools such as Python libraries (e.g., Pandas, NumPy) | Shubham Gaikwad | 2023-09-11 |  | 2023-09-11 | 2 | Completed | Task Finished | NA
4.6 | Week 7 |  |  | Data Analysing | Understanding of statistical concepts and analysis techniques. | Shubham Gaikwad | 2023-09-12 |  | 2023-09-12 | 2 | Completed | Task Finished | NA
| Week 7 |  |  | Solving Problem Statement | Knowledge of different problem-solving frameworks or methodologies. | Shubham Gaikwad | 2023-09-13 |  | 2023-09-14 | 3 | Completed | Task Finished | NA
| Week 7 |  |  | Visualization | Visualization libraries/tools (e.g., Matplotlib, Plotly, seaborn) to create charts, graphs, and interactive visualizations. | Shubham Gaikwad | 2023-09-15 |  | 2023-09-16 | 3 | Completed | Task Finished | NA
4.7 | Week 7 |  | Weekly Meeting Attended | - | Schedule and coordination of meeting times. | Shubham Gaikwad | 2023-09-16 |  | 2023-09-16 | 2 | Completed | Attended | NA
5 |  | Code Testing |  |  |  |  | 2023-09-18 | 2023-09-23
5.1 | Week 8 |  | Testing Code Manually | - | Code or program to be tested, and Test cases | Shubham Gaikwad | 2023-09-18 |  | 2023-09-22 | 2 | Completed | Task Finished | NA
5.2 | Week 8 |  | Weekly Meeting Attended | - | Schedule and coordination of meeting times. | Shubham Gaikwad | 2023-09-23 |  | 2023-09-23 | 2 | Completed | Attended | NA
6 |  | Project Closure |  |  |  |  | 2023-09-25 | 2023-09-30
| Week 9 |  | Final Project Report | - | Project documentation,Project deliverables | Shubham Gaikwad | 2023-09-26 |  |  | 2 | Completed | Task Finished | NA
| Week 9 |  | Project Submition | - | Submission guidelines and Timeline | Shubham Gaikwad | 2023-09-29 |  |  | 1 | Completed | Task Finished | NA
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you